## README
Tracker — format legend
Nesting: the column a name sits in is its kind — Project (col A), Milestone (B), Goal (C), Task (D).
Each project has its own sheet; orphan planner tasks live on the Planner sheet.
Task order within a goal is top-to-bottom and strictly sequential by default.
Parallel exception: tasks sharing a Seq number (highlighted yellow) form a parallel group.
Depends on: prerequisite goals/tasks by name, any sheet. The Ref column holds each row's canonical id;
dependencies are stored against those ids, so renaming a row never breaks a link.
Deadlines cascade: a row inherits the earliest deadline of any row above it in its nesting chain.
Example row values: a task row has only column D filled, plus Seq, Est (min), and optionally
Depends on / Deadline / Tags / Notes. Kind rows (A–C) carry only name, deadline, notes.

## Licensing & Compliance
Project | Milestone | Goal | Task | Seq | Depends on | Deadline | Est (min) | Tags | Notes | Ref
Licensing & Compliance | [5 empty] | 2026-09-30 |  |  | Shared prerequisite project — several goals here block other projects | OPS
| Legal foundation |  |  |  |  | 2026-08-31 |  |  |  | OPS.M1
|  | Form business entity | [7 empty] | OPS.M1.entity
|  |  | Choose business structure with accountant | 1 |  |  | 120 | desk;call | LLC vs S-corp decision | OPS.M1.entity.t1
|  |  | File LLC formation | 2 |  |  | 90 | admin |  | OPS.M1.entity.t2
|  |  | Obtain EIN | 3 |  |  | 30 | admin |  | OPS.M1.entity.t3
|  |  | Open business bank account | 4 |  |  | 90 | errand |  | OPS.M1.entity.t4
|  | Secure permits & licenses |  |  | Form business entity | 2026-08-31 |  |  | Blocks first roast and cafe opening | OPS.M1.permits
|  |  | Draft license & permit applications | 1 |  |  | 180 | admin;deep |  | OPS.M1.permits.t1
|  |  | Submit applications & pay fees | 2 |  |  | 60 | admin |  | OPS.M1.permits.t2
|  |  | Schedule fire inspection | 3 |  |  | 30 | call | Parallel with t4 (same seq) | OPS.M1.permits.t3
|  |  | Schedule health inspection | 3 |  |  | 30 | call | Parallel with t3 (same seq) | OPS.M1.permits.t4
|  |  | Pass inspections & receive permits | 4 |  |  | 120 | site |  | OPS.M1.permits.t5
| Insurance & finance |  |  |  |  | 2026-09-30 |  |  |  | OPS.M2
|  | Business insurance | [7 empty] | OPS.M2.insure
|  |  | Request quotes from three brokers | 1 |  |  | 90 | call |  | OPS.M2.insure.t1
|  |  | Compare coverage & pick policy | 2 |  |  | 60 | desk |  | OPS.M2.insure.t2
|  |  | Bind policy | 3 |  |  | 45 | admin |  | OPS.M2.insure.t3
|  | Accounting setup |  |  | Form business entity |  |  |  |  | OPS.M2.books
|  |  | Choose accounting software | 1 |  |  | 90 | desk |  | OPS.M2.books.t1
|  |  | Build chart of accounts | 2 |  |  | 120 | deep |  | OPS.M2.books.t2
|  |  | Hire part-time bookkeeper | 3 |  |  | 180 | call |  | OPS.M2.books.t3

## Roastery Buildout
Project | Milestone | Goal | Task | Seq | Depends on | Deadline | Est (min) | Tags | Notes | Ref
Roastery Buildout | [5 empty] | 2026-11-15 |  |  | Production facility | RST
| Facility ready |  |  |  |  | 2026-10-01 |  |  |  | RST.M1
|  | Secure facility |  |  | Form business entity |  |  |  | Entity must exist to sign the lease | RST.M1.lease
|  |  | Tour candidate spaces | 1 |  |  | 240 | errand |  | RST.M1.lease.t1
|  |  | Negotiate lease terms | 2 |  |  | 180 | call |  | RST.M1.lease.t2
|  |  | Sign lease | 3 |  |  | 60 | admin |  | RST.M1.lease.t3
|  | Buildout |  |  | Secure facility | 2026-10-01 |  |  |  | RST.M1.build
|  |  | Design floor layout | 1 |  |  | 240 | deep |  | RST.M1.build.t1
|  |  | Hire contractor | 2 |  |  | 180 | call |  | RST.M1.build.t2
|  |  | Electrical & gas upgrades | 3 |  |  | 480 | site | Parallel with t4 (same seq) | RST.M1.build.t3
|  |  | Ventilation installation | 3 |  |  | 480 | site | Parallel with t3 (same seq) | RST.M1.build.t4
|  |  | Final walkthrough & punch list | 4 |  |  | 120 | site |  | RST.M1.build.t5
| Production online |  |  |  |  | 2026-11-15 |  |  |  | RST.M2
|  | Install roaster |  |  | Buildout |  |  |  |  | RST.M2.roaster
|  |  | Purchase roaster | 1 |  |  | 120 | desk |  | RST.M2.roaster.t1
|  |  | Coordinate freight & delivery | 2 |  |  | 60 | call |  | RST.M2.roaster.t2
|  |  | Install & vent hookup | 3 |  |  | 300 | site |  | RST.M2.roaster.t3
|  |  | Calibrate & run seasoning roasts | 4 |  |  | 240 | deep |  | RST.M2.roaster.t4
|  | Source green beans | [6 empty] | No deps — runs parallel to the buildout | RST.M2.beans
|  |  | Shortlist importers | 1 |  |  | 120 | desk |  | RST.M2.beans.t1
|  |  | Request samples | 2 |  |  | 60 | admin |  | RST.M2.beans.t2
|  |  | Cup samples | 3 |  |  | 180 | deep |  | RST.M2.beans.t3
|  |  | Negotiate supply contract | 4 |  |  | 120 | call |  | RST.M2.beans.t4
|  |  | Place first order | 5 |  |  | 45 | admin |  | RST.M2.beans.t5
|  | First production roast |  |  | Install roaster; Source green beans; Secure permits & licenses | 2026-11-15 |  |  | Limiting step — blocks cafe menu; barista training; and wholesale | RST.M2.roast
|  |  | Develop roast profiles | 1 |  |  | 360 | deep |  | RST.M2.roast.t1
|  |  | Run test batches | 2 |  |  | 300 | deep |  | RST.M2.roast.t2
|  |  | QA cupping | 3 |  |  | 120 | deep |  | RST.M2.roast.t3
|  |  | Lock production profiles | 4 |  |  | 90 | desk |  | RST.M2.roast.t4

## Cafe Launch
Project | Milestone | Goal | Task | Seq | Depends on | Deadline | Est (min) | Tags | Notes | Ref
Cafe Launch | [5 empty] | 2026-12-05 |  |  | Front-of-house in the roastery building | CAF
| Space & menu |  |  |  |  | 2026-11-20 |  |  |  | CAF.M1
|  | Cafe fit-out |  |  | Secure facility |  |  |  |  | CAF.M1.fitout
|  |  | Design cafe interior | 1 |  |  | 300 | deep |  | CAF.M1.fitout.t1
|  |  | Order furniture & fixtures | 2 |  |  | 120 | admin |  | CAF.M1.fitout.t2
|  |  | Counter & bar install | 3 |  |  | 480 | site |  | CAF.M1.fitout.t3
|  |  | Espresso machine install & water line | 4 |  |  | 240 | site |  | CAF.M1.fitout.t4
|  | Menu development | [7 empty] | CAF.M1.menu
|  |  | Draft menu | 1 |  |  | 180 | deep |  | CAF.M1.menu.t1
|  |  | Cost & price items | 2 |  |  | 120 | desk |  | CAF.M1.menu.t2
|  |  | Tasting with production coffee | 3 | task: Lock production profiles |  | 180 | deep | Task-level dep — needs locked profiles; not the whole goal chain | CAF.M1.menu.t3
|  |  | Finalize & print menus | 4 |  |  | 90 | admin |  | CAF.M1.menu.t4
| Opening |  |  |  |  | 2026-12-05 |  |  |  | CAF.M2
|  | Hire & train staff | [7 empty] | CAF.M2.staff
|  |  | Write & post job listings | 1 |  |  | 120 | desk |  | CAF.M2.staff.t1
|  |  | Run interviews | 2 |  |  | 360 | call |  | CAF.M2.staff.t2
|  |  | Make offers | 3 |  |  | 90 | call |  | CAF.M2.staff.t3
|  |  | Barista training on house coffee | 4 | task: Lock production profiles |  | 480 | site | Task-level dep on locked profiles | CAF.M2.staff.t4
|  | Soft open |  |  | Cafe fit-out; Menu development; Hire & train staff; Secure permits & licenses; Business insurance | 2026-12-05 |  |  | Converges five goals across three projects | CAF.M2.open
|  |  | Dry-run service day | 1 |  |  | 300 | site |  | CAF.M2.open.t1
|  |  | Friends & family night | 2 |  |  | 240 | site |  | CAF.M2.open.t2
|  |  | Work the fix list | 3 |  |  | 240 | site |  | CAF.M2.open.t3
|  |  | Public opening day | 4 |  |  | 480 | site |  | CAF.M2.open.t4

## Wholesale Line
Project | Milestone | Goal | Task | Seq | Depends on | Deadline | Est (min) | Tags | Notes | Ref
Wholesale Line | [5 empty] | 2026-12-18 |  |  |  | WHL
| Brand & packaging |  |  |  |  | 2026-11-01 |  |  |  | WHL.M1
|  | Brand identity | [7 empty] | WHL.M1.brand
|  |  | Hire designer | 1 |  |  | 120 | call |  | WHL.M1.brand.t1
|  |  | Logo & visual identity rounds | 2 |  |  | 120 | desk |  | WHL.M1.brand.t2
|  |  | Retail bag design | 3 |  |  | 90 | desk |  | WHL.M1.brand.t3
|  |  | Order printed bags | 4 |  |  | 60 | admin |  | WHL.M1.brand.t4
|  | Wholesale pricing |  |  | Accounting setup |  |  |  | Needs real cost data from the books | WHL.M1.price
|  |  | Build cost model | 1 |  |  | 240 | deep |  | WHL.M1.price.t1
|  |  | Tiered price sheet | 2 |  |  | 90 | desk |  | WHL.M1.price.t2
| First accounts |  |  |  |  | 2026-12-18 |  |  |  | WHL.M2
|  | Sales pipeline |  |  | First production roast; Brand identity; Wholesale pricing | 2026-12-18 |  |  |  | WHL.M2.pipeline
|  |  | Build prospect list | 1 |  |  | 180 | desk |  | WHL.M2.pipeline.t1
|  |  | Assemble sample kits | 2 |  |  | 120 | site |  | WHL.M2.pipeline.t2
|  |  | Outreach emails & calls | 3 |  |  | 240 | call |  | WHL.M2.pipeline.t3
|  |  | On-site tastings | 4 |  |  | 360 | errand |  | WHL.M2.pipeline.t4
|  |  | Close first three accounts | 5 |  |  | 240 | call |  | WHL.M2.pipeline.t5

## Planner
Project | Milestone | Goal | Task | Seq | Depends on | Deadline | Est (min) | Tags | Notes | Ref
|  |  | Pay Q3 estimated taxes |  |  | 2026-09-15 | 90 | admin | Orphan planner task — no parent | inbox.q3-taxes
|  |  | Send July consulting invoices |  |  | 2026-08-05 | 60 | admin | Orphan planner task | inbox.invoice-jul
|  |  | Email broker re: equipment loan |  |  | 2026-08-01 | 20 | call | Orphan planner task | inbox.email-broker
|  |  | Renew delivery van insurance |  |  | 2026-10-10 | 45 | admin | Orphan planner task | inbox.van-insurance
|  |  | Book dentist appointment |  |  | 2026-08-20 | 15 | call | Orphan planner task | inbox.dentist