## Licensing & Compliance
Project | Milestone | Goal | Task | Notes
Licensing & Compliance |  |  |  | a lot of the other projects wait on things in here
Legal foundation
Form business entity
Choose business structure with accountant
File LLC formation
Obtain EIN
Open business bank account
|  | Secure permits & licenses |  | start after the entity stuff is done
Draft license & permit applications
Submit applications & pay fees
|  |  | Schedule fire inspection | fire and health scheduling can happen the same week
Schedule health inspection
Pass inspections & receive permits
Insurance & finance
Business insurance
Request quotes from three brokers
Compare coverage & pick policy
Bind policy
|  | Accounting setup |  | needs the LLC
Choose accounting software
Build chart of accounts
Hire part-time bookkeeper

## Roastery Buildout
Project | Milestone | Goal | Task | Notes
Roastery Buildout
Facility ready
|  | Secure facility |  | need the LLC before signing anything
Tour candidate spaces
Negotiate lease terms
Sign lease
|  | Buildout |  | once we have the space
Design floor layout
Hire contractor
|  |  | Electrical & gas upgrades | electrical and ventilation can run at the same time
Ventilation installation
Final walkthrough & punch list
Production online
|  | Install roaster |  | buildout has to be finished first
Purchase roaster
Coordinate freight & delivery
Install & vent hookup
Calibrate & run seasoning roasts
|  | Source green beans |  | can chip away at this while the buildout happens
Shortlist importers
Request samples
Cup samples
Negotiate supply contract
Place first order
|  | First production roast |  | needs the roaster in, beans on hand, and permits sorted — this one gates a lot
Develop roast profiles
Run test batches
QA cupping
Lock production profiles

## Cafe Launch
Project | Milestone | Goal | Task | Notes
Cafe Launch
Space & menu
|  | Cafe fit-out |  | same building as the roastery, so need that lease
Design cafe interior
Order furniture & fixtures
Counter & bar install
Espresso machine install & water line
Menu development
Draft menu
Cost & price items
|  |  | Tasting with production coffee | can't do the tasting until roast profiles are locked
Finalize & print menus
Opening
Hire & train staff
Write & post job listings
Run interviews
Make offers
|  |  | Barista training on house coffee | needs finished coffee to train on
|  | Soft open |  | everything converges here — fitout, menu, staff, permits, insurance
Dry-run service day
Friends & family night
Work the fix list
Public opening day

## Wholesale Line
Project | Milestone | Goal | Task | Notes
Wholesale Line
Brand & packaging
Brand identity
Hire designer
Logo & visual identity rounds
Retail bag design
Order printed bags
|  | Wholesale pricing |  | need real cost numbers out of the books first
Build cost model
Tiered price sheet
First accounts
|  | Sales pipeline |  | needs coffee, brand, and pricing in place
Build prospect list
Assemble sample kits
Outreach emails & calls
On-site tastings
Close first three accounts

## Planner
Task | Notes
Pay Q3 estimated taxes
Send July consulting invoices
Email broker re: equipment loan
Renew delivery van insurance
Book dentist appointment